## Timeline
Project Name |  | Total Duration(Days) | Start Date | End Date | Submission date
Vacation Spot Development and Property Renting |  | 20 | 2021-09-01 | 2021-09-26
Sl No. | Task Descriptions | Start Date | End Date | Duration
1 | Planning/Design
1.1 | Project Defination | 2021-08-28 | 2021-08-31 | 3
1.2 | Finish webpage | 2021-08-31 | 2021-09-03 | 3
1.3 | Project Design | 03-90-2021 | 2021-09-05 | 2
2 | Coding
2.1 | Phase 1 | 2021-09-05 | 2021-09-09 | 4
2.2 | Phase 2 | 2021-09-09 | 2021-09-13 | 4
2.3 | Additional Features | 2021-09-14 | 2021-09-18 | 4
3 | Testing
3.1 | Phase 1 Testing | 2021-09-19 | 2021-09-20 | 2
3.2 | Modification /Any changes | 2021-09-20 | 2021-09-21 | 1
3.3 | Phase 2 Testing | 2021-09-21 | 2021-09-22 | 1
3.4 | Modification /Any changes | 2021-09-22 | 2021-09-24 | 2
3.5 | Final Testing | 2021-09-24 | 2021-09-25 | 1
4 | Documentation
4.1 | User Guide | 2021-09-25 | 2021-09-26 | 1
4.2 | Presentation | 2021-09-25 | 2021-09-26 | 1

## Roles & Responsiblity
Roles And Responsiblities
1 | Role | Team Leader
| Member Name | Prasad Sudhakar Shinde
| PRN No | 210543181122
| Description | Design and planning, front & Back end , testing ,Documentation
2 | Role | Team Member
| Member Name | Vikas Shashikant Kumbhar
| PRN No | 210543181049
| Description | Design and planning, front & Back end , testing ,Documentation
3 | Role | Team Member
| Member Name | Suraj Vilas Bavdekar
| PRN No | 210543181121
| Description | Design and planning, front & Back end , testing ,Documentation
4 | Role | Team Member
| Member Name | Rushikesh Ravindra Kadam
| PRN No | 210543181033
| Description | Design and planning, front & Back end , testing ,Documentation